## Rubin Funding
Appropriated and Requested MREFC Funds for
Vera C. Rubin Observatory
(Dollars in Millions)
| Prior Years | FY 2019 | FY 2020 | FY 20211 | FY 2022 | FY 20232 Estimate | FY 2024 Request2 | Total Project
Previous Authorized Total Project Cost | 331.72 | 48.82 | 46.35 | 40.75 | 5.36 | 0 | 0 | 473
Current Authorized Total Project Cost (COVID-19) | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 10
Preliminary Estimate of Future COVID-19 Impact | 0 | 0 | 0 | 0 | 35.39 | 15 | 7.61 | 58
American Rescue Plan | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 30
Estimate after Rebaseline | 331.72 | 48.82 | 56.35 | 70.75 | 40.75 | 15 | 7.61 | 571
1 In December 2021, based on the recent re-baseline of the Rubin construction project, NSB authorized a new Total Project Cost of $571.0 million.
2 The FY 2023 appropriation, together with the FY 2024 Request, are based on the current best estimate of the total funding needed to address COVID-19 impacts. The COVID-19 situation continues to evolve, and ongoing schedule and cost impacts may lead to revisions of this funding plan.