## Sheet1
MREFC Account Funding
(Dollars in Millions)
| FY 2006 Actual | FY 2007 Request | FY 2008 Request | FY 2009 Estimate | FY 2010 Estimate | FY 2011 Estimate | FY 2012 Estimate | FY 2013 Estimate
Ongoing Projects
ARRV1 |  | 56 | 42 | 25 | 0
ALMA2 | 48.6561 | 64.27 | 102.07 | 74.75 | 42.76 | 21.44 | 3 | 0
DOJ Judgment |  | 3 | 0
EarthScope | 49.6156 | 27.4 | 0
IceCube | 56.4398 | 28.65 | 22.38 | 11.33 | 0.95 | 0
NEON3 |  | 4 | 8 | 20 | 30 | 26 | 12 | 0
OOI4 |  | 5.12 | 30.99 | 80 | 90 | 95 | 30 | 0
SODV | 66.0336 | 42.88 | 0
SPSM5 | 13.069 | 9.13 | 6.55 | 0
New Starts
AdvLIGO6 |  | 0 | 32.75 | 51.43 | 46.3 | 15.21 | 23.73 | 15.5
MREFC Account Total | 233.8141 | 240.45 | 244.74 | 262.51 | 210.01 | 157.65 | 68.73 | 15.5
Totals may not add due to rounding. 1The recent baseline analysis for ARRV noted the potential for a cost increase of $25.0 million (included in FY 2009). 2ALMA is increased by $16.38 million in FY 2007 following a rebaselining completed in FY 2006. Figures for FY 2008 and beyond also reflect the new baseline. 3NEON is reduced in FY 2007 to partially cover ALMA's increase. NEON's revised baseline is expected in May 2007 following a Preliminary Design Review (PDR). The amount in FY 2012 reflects the reduced funding in FY 2007 and FY 2008. 4OOI is reduced by $8.38 million in FY 2007 to cover the remainder of ALMA's increase. OOI plans to conduct a PDR in December 2007, at which time firmer cost estimates will be available. 5The SPSM cost to complete was updated in August 2006. The revised work plan, schedule and estimate were reviewed in detail by an external panel in September 2006 and the estimate for FY 2008 reflects the cost to complete the remaining scope of the project in accordance with the revised schedule. 6The AdvLIGO estimate reflects the formal project baseline reviewed by the external panel convened by NSF in June 2006.