## NEON Funding Requirements
Total Funding Requirements for NEON
(Dollars in Millions)
| Prior Years1 | FY 2016 Actual | FY 2017 Estimate | FY 2018 Request | ESTIMATES
[5 empty] | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023
R&RA:
Concept & Development | 104.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Operations & Maintenance2,3 | 21 | 32.972 | 65 | 65 | 65 | 65 | 65 | 65 | 65
ARRA | 9.9628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal, R&RA | 135.8128 | 32.972 | 65 | 65 | 65 | 65 | 65 | 65 | 65
MREFC:
Implementation3,4 | 296.8755 | 128.5111 | 43.91 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL REQUIREMENTS | 432.6884 | 161.4831 | 108.91 | 65 | 65 | 65 | 65 | 65 | 65
1 Concept & Development funding and Implementation funding are cumulative of all prior years; Operations & Maintenance (O&M) funding reflects prior year actual obligations only.
2 Funding for O&M is currently capped at $65.0 million per year for planning purposes, pending the results from an initial period of operations under Battelle management. Future O&M requests will be based on a more thorough analysis of science capabilities and affordability.
3 Consistent with revised TPC plans, $20.0 million of FY 2016 R&RA appropriated funding was transferred to the MREFC account and carried forward into FY 2017. Up to $15.58 million of FY 2017 R&RA requested funding is expected to be transferred into the MREFC account.
4 $56.0 million of FY 2015 MREFC funding for NEON was carried over into FY 2016. A total of $28.41 million of FY 2016 MREFC funding was carried over into FY 2017 of which $8.40 million is being held as part of NSF’s strengthened oversight of budget contingency as well as NSF-held management reserve. These funds will be made available to the project based on bona fide need and recipient performance.