## Slide 1: Development of the NSF Process for Validation and Acceptance of Facility Project EVMS
Large Facilities Workshop 2016
Earned Value Management –
Certification or Verification?
Breakout Session

## Slide 2: Purpose and Goals
NSF is establishing guidelines and requirements for Earned Value Management Systems (EVMS) for evaluating construction project status and management. Other federal agencies have established EVMS requirements, with varying ranges of rigor, depth of inspection, and involvement by external EVM professionals, that are based upon the 32 EIA Standard 748 guidelines.
Please provide thoughts and experiences on the impacts and benefits of EVMS evaluation to inform development of NSF EVM guidance and requirements for the 2017 revision to the LFM.

## Slide 3: IG Recommendations for EVMS Validation and Certification:
“Obtain certification of AURA’s EVM system for LSST and validate EVM data for LSST” OIG Alert Memo #15-3-001
“Validat(e) AURA’s EVM data for DKIST, and certify AURA’s EVM system.” ” OIG Alert Memo #16-3- 004
“In light of the critical insights robust EVM data can provide those managing and overseeing projects, NSF should …. take decisive action to ensure the quality of EVM data on all its large construction projects.” IG to US house of Representatives Subcommittee on Research and Technology, Feb 4, 2016

## Slide 4: IG Comments on EVMS Validation and Certification: OIG Alert Memos #15-3-001 and 16-3-004
“Certification of an EVM system is needed to ensure that an awardee maintains an acceptable EVM system, which includes data to support scheduling of work and interim progress measures, among other things. Our examination of thresholds other federal agencies use when determining whether an awardee’s EVM system should be certified found thresholds of $10 million and $50 million….”
“Certification of an EVM system, including supporting data, is conducted by the Defense Contract Management Agency to ensure that an awardee maintains an acceptable EVM system..”

## Slide 5: Terms
Validation: review and acceptance for compliance with EIA-748
Certification: typically refers to the DOD one-time issuance of a letter of acceptance by DCMA after validation. (once certified, EVMS can be used for multiple projects.)
Surveillance: periodic reviews to verify proper implementation after initial validation and acceptance

## Slide 6: Federal Agency Practices
DOD, NASA use DMCA validation/certification requirements and DCMA professionals
Many Non-DOD agencies use self-validation, peer validation, or other third-party validation according to various thresholds.
  Third-party validation by EVM professionals most desirable for ‘large capital acquisitions’
  Acceptance/approval methods vary
  Validations can take months and $$$ - normally consist of initial visits, progress assistance visits for project corrections, and actual validation reviews (names vary by performing agency).

## Slide 7: NSF Response to IG
NSF is evaluating the benefits of EVM system validation/certification as a requirement for facilities projects.
LFO performed a pilot validation of EVM data for LSST as part of the 2016 annual review process.
LFO is drafting a Standard Operating Guide (SOG) for EVMS Validation
Seeking community input on the impacts and benefits of EVMS validation implementation

## Slide 8
  WBS
  WBS
  WBS Definition
  WBS Dictionary (SOW)
  COST MODEL
  DATA SET
  Cost Estimates
  Staffing levels
  Rate tables/ inputs
  BOE
  GR&A
  Risk Assessments
  Cost Accounts
  Sorting IDs and codes
  SOW (WBS )
  Cost Book Reports
  Cost Book Sheets
  CB Summaries
  ICA reports
  Integrated Master Schedule
  WBS-based activities
  Duration Estimates
  Logic and relationships
  Resources from BOE Data Base
  Risk analysis inputs
  Sorting and group codes
  Project Calendars
  ETC projections
  Schedule Reports
  Schedules/Summaries
  Critical and Longest Paths
  Progress reports
  Staffing Plans
  Time Phased Budget
  Escalation
  EAC/ETC
  CPRD
  NSF 1030 forms
  Earned Value Management
  Time-phased Target Baseline
  Actuals input from Accounting
  Contingency Management
  EAC/ETC management
  Risk analysis inputs and analysis
  Sorting and group codes
  Project Calendars
  Risk Reports
  Risk S-curves
  Contingency Confidence Levels
  Risk Exposure
  Risk Ranking
  Mitigation impacts
  Risk Analysis Tools
  Monte Carlo Simulation
  EVM Reports
  Then-Year Budgets
  TPC
  Monthly EVM reports
  Budget Summaries
  CPRD
  ICA reports
  NSF 1030 forms
  Institutional Accounting Systems
  Actuals
  Commitments
  Procurements Info
  Funding
  Account Structures
Excel, Word, etc.
Excel, Access, MySQL, FileMaker Pro, etc.
Primavera, MS Project, etc.,
Primavera, Cobra, etc.,
PRM, Polaris, @RISK, etc.,
Oracle, Deltek, etc.,
Project Management Control/EVM Systems Flow Chart
July 23, 2015 v-2

## Slide 9: NSF Pilot EVMS Evaluation of LSST
Conducted in tandem but separate from annual review
3 Reviewers: certified EVM professional contractor, LFO staffer, and SME for telescope projects
  Did not use DCMA reviewers
3 weeks of EVMS document reviews
2 days of on site interviews – AURA and LSST staff
Issued report stating ‘In compliance with areas for improvement’ (not exactly acceptance/certification)
Project response by next annual review (late 2016)
Repeat surveillance by reviewing implementation at time of 2017 annual review
Duration ~ 5 weeks with Cost to program ~$10K

## Slide 10: Pilot Review Process
Review documents for compliance with the 32 EIA-478 standards
Interview project accounting, project controls, and project team members for knowledge and proper implementation against documentation and EIA-478 standards
Use interview templates for consistency
Fill out EIA-478 checklist and report findings

## Slide 11: Steps to SOG
Decide whether NSF uses DCMA certification or it’s own version of written “acceptance/approval”
Settle on thresholds and processes for review -> correct -> final review and acceptance/approval, including designating approvers
Agree on qualifications and number of reviewers (3rd party EVMP versus DCMA)
Improve interview templates and EIA-checklist as needed; create standard report and “acceptance” letter templates
Determine timing and requirements for initial and follow-up surveillance reviews.
Determine who pays for validation and surveillance reviews
Differentiate deeper dive for initial review (pre-FDR) from surveillance reviews=> larger initial burden (time and money)
Likely to require project implementation of EVM tools and processes during Final Design phase in order to be able to pass initial EVM validation as part of FDR.
Determine process for dealing with chronic non-compliance