## Slide 1: 2016 NSF Large Facilities Workshop New Initiatives Business Roundtable II-III May 25-26, 2016
Jeff Lupis, Division Director, Division of Acquisition and Cooperative Support
jlupis@nsf.gov (703) 292-7944

## Slide 2: Purpose of Briefing:
Discuss background and context of the current environment of strengthened cost oversight of NSF large facility awards
Discuss four specific areas of strengthened cost oversight
Solicit awardee insights and concerns with the award oversight process
Look to improve the business oversight process going forward

## Slide 3: Background/Context
In 2004, responsibility for large facility cooperative agreements was moved to the “Division of Contracts and Complex Agreements”
In FY 2010, NSF’s Financial Statement Audit cited a large facility cooperative agreement where $88M in questioned contingency costs were reported
Beginning in FY 2011, NSF’s Financial Statement Audit has included a Significant Deficiency titled “Monitoring of Construction Type Cooperative Agreements,” expanding findings from the 2010 audit
NSF’s efforts to ensure the proper level of cost oversight, as well as outside concerns raised by NSF Stakeholders, has driven a close examination and strengthening of business procedures for managing these awards

## Slide 4: Background/Context (Cont.)
OIG Alert Memo “NSF’s Management of Cooperative Agreements,” (Sept. 2012) highlighted concerns with both pre-award and post-award monitoring processes. Recommendations for awards over $50M included:
  Obtaining proposal and accounting systems audits for all planned large facility cooperative agreements
  Requiring annual incurred cost submissions and audits
  Requiring awardees to properly account for and separately track budgeted versus actual contingency use
The OIG has issued additional alert memos and audit reports highlighting concerns under specific NSF large facility awards

## Slide 5: Four Areas of Strengthened Procedures:
Proposal and Accounting System Reviews/Audits
Incurred Cost Audits
Contingency Management
Risk-Based End-to-End Cost Surveillance Policies

## Slide 6: Proposal and Acct. System Reviews/Audits
Strengthened Procedure:
More detailed pre-award evaluation of proposal cost estimates and review (or audit) of awardee cost accounting systems/practices prior to awarding CAs
Implementation:
NSF Standard Operating Guidance (SOG) requires the completion of a Cost Proposal Review Document (CPRD) for all awards over $100M, documenting cost analysis and review of awardee’s accounting system
Thorough review of the budget estimate will be completed on a cost element basis (FDR stage)
Guidance updated in 2015 to include reviews at CDR and PDR phases

## Slide 7: Proposal and Acct. System Reviews/Audits (Cont.)
Additional guidance included in Large Facilities Manual on format and detail required for construction and operations proposals
Supportability of proposal is key
Proposal audits are to be obtained when determined necessary
NSF will execute independent cost assessments for construction awards > $100M
The CPRD will document review of awardee accounting system
  Note: NSF will obtain audits of awardees’ accounting systems/practices prior to entering into construction CA’s totaling $100M or more, where NSF is the cognizant agency and such an audit has not been performed within the past two years.

## Slide 8: Proposal and Acct. System Reviews/Audits (Cont.)
Note: 2 CFR 200 requires that agencies awarding cooperative agreements must have in place a framework for evaluating the risks posed by applicants before they receive Federal awards. Examples of areas to be reviewed include:
Financial stability
History of performance
Reports and findings from audits performed under the Uniform Guidance Audit Requirements and findings from any other available audits
Notes: *I’ve told you WHAT the talk is about
*WHO we are
*Now how we’re going to present the information which includes the input we need from audience members

## Slide 9: Incurred Cost Audits
Strengthened Procedure:
Requirements for incurred cost audits
Implementation:
NSF will require, at a minimum, a final review of incurred costs at project completion for large facility projects totaling $100M or more
NSF will use risk analysis on a project-by-project basis to determine whether additional incurred cost audits are needed during a project
NSF committed to explore best practices and to complete an analysis and recommendation for awardee cost submissions (now completed)

## Slide 10: Incurred Cost Audits (Cont.)
Pre-award, the CPRD requires an initial determination of the need for an incurred cost audit
Post-award, a separate SOG has institutionalized NSF’s project-by-project annual review of the need for incurred cost audits during performance
With transition of audit process to NSF’s cognizance (and unavailability of DCAA to complete audits), NSF is working to obtain audit support services
Recipients should be prepared for such an audit at any time based on requirements set forth in 2 CFR 200
NSF completed a review of best practices for incurred cost submissions and determined a perspective award provision and cost data collection tool

## Slide 11: Incurred Cost Audits (Cont.):
In preparation for a cost incurred audit, recipients will be required to submit financial expenditures (incurred cost) data to NSF
The Financial Data Collection Tool was created by NSF to assist recipients in preparing and recording financial expenditure information
This tool will be required for submission of the financial expenditures data
The Financial Data Collection Tool is a macro-enabled Excel workbook that provides recipients a single, standardized method for submitting cost data
Notes: *I’ve told you WHAT the talk is about
*WHO we are
*Now how we’re going to present the information which includes the input we need from audience members

## Slide 12: Incurred Cost Audits (Cont.): Large Facilities Financial Data Collection Tool
Notes: Effort evolves as the awardee’s cost estimate evolves through these preconstruction stages.

## Slide 14: Incurred Cost Audits (Cont.): Large Facilities Financial Data Collection Tool
The Large Facilities Manual and the Large Facilities Financial Data Collection Tool can be viewed on the public NSF webpage at:
https://www.nsf.gov/bfa/lfo/lfo_documents.jsp
To provide comments on the Large Facilities Manual and the Large Facilities Financial Data Collection Tool, please go to the Federal Register at:
https://www.gpo.gov/fdsys/pkg/FR-2016-05-09/pdf/2016-10793.pdf
Notes: *I’ve told you WHAT the talk is about
*WHO we are
*Now how we’re going to present the information which includes the input we need from audience members

## Slide 15: Contingency
Strengthened Procedure:
Contingency management
Implementation:
Standardized guidance for contingency estimating in the Large Facilities Manual
Supportability of the estimate is key
NSF Completed a review of the controls and thresholds for the Change Control Board (CCB) process

## Slide 16: Contingency (Cont.)
Standardized reporting of contingency in monthly project reports and the bi-monthly large facilities status report
New standardized award provision to clearly identify the NSF approved contingency budget and incremental allocations to the Recipient
New SOG to incorporate the NAPA recommendation that NSF retain control of a portion of contingency (up to 100%) based on the circumstances of the award

## Slide 17: End-to-End Cost Surveillance Policies
Strengthened Procedure:
Development of a risk-based approach for end-to-end cost surveillance
Implementation:
NSF chose the threshold of $100M to focus on the highest risk awards
NSF committed to expand the scope of strengthened procedures to large facility operations by September 15, 2015 (completed)
After implementation, NSF will invite a qualified third-party organization to evaluate the results

## Slide 18: End-to-End Cost Surveillance Policies
BFA continues to strengthen cost estimating and cost monitoring oversight procedures through issuance and update of numerous SOGs, e.g.,:
  SOG 15-1 Negotiation, Award and Payment of Management Fee
  SOG 15-6 Guidance on Pre and Post-Award Cost Monitoring Procedures
  SOG 16-2 Budget Contingency Obligation and Allocation
  SOG 16-4 DACS CSB Standardized Cost Analysis Guidance
NSF is further evaluating cost oversight procedures considering subsequent internal evaluation and Stakeholder input

## Slide 19: Additional Issues Identified
Additional issues identified through:
Internally determined areas for improvements
Ongoing interactions with Stakeholders
National Academy of Public Administration (NAPA) Report “Use of Cooperative Agreements to Support Large Scale Investment in Research”
Additional issues include but are not limited to:
Proper use of management fee
Conducting awardee estimating system reviews

## Slide 20
Questions?
Concerns?
Other Issues?